## Sheet1
Project Name	Stair Climbing Rescue Robot					key	Meetings
Student	Daniel Stares					Research
Student ID	10560118					Hardware
Project Supervisor(PS)	David Jenkins					Software
				Deadline
	Date(week commencing)		October				November				December				January				Febuary				March				April				May				Planning
Stages	Tasks:	7th	14th	21st	28th	4th	11th	18th	25th	2nd	9th	16th	23rd	6th	13th	20th	27th	3rd	10th	17th	24th	2nd	9th	16th	23rd	6th	13th	20th	27th	4th	11th	18th	25th
	Discuss initial project idea
Stage 1	Research initial project idea
Initial Ideas	Initial Project Proposal (16/10/19)
& Planning	Discuss final project idea with PS
	Research final project idea
	Final Project Proposal (30/10/19)
	Research field
	Research motors
Stage 2	Research movement options
Research	Research develepment boards
	Research power sources for project
	Research control methods
	Order initial components
	Design base of robot
Stage 3	Code for gyro scope
CAD design and Code	Replicate motors in CAD
	Design tracks and related components in CAD
	Design simulation environment in CAD
	Robot Properties
	Full assembly of robot in CAD

	Simulation of robot in CAD
Stage 4
Simulation

Stage 5 - Report