## Sheet1
Project Name	Stair Climbing Rescue Robot					key	Meetings
Student	Daniel Stares					Research
Student ID	10560118					Hardware
Project Supervisor(PS)	David Jenkins					Software
				Deadline
	Date(week commencing)		October				November				December				January				Febuary				March				April				May				Planning
Stages	Tasks:	7th	14th	21st	28th	4th	11th	18th	25th	2nd	9th	16th	23rd	6th	13th	20th	27th	3rd	10th	17th	24th	2nd	9th	16th	23rd	6th	13th	20th	27th	4th	11th	18th	25th
	Discuss initial project idea
Stage 1	Research initial project idea
Initial Ideas	Initial Project Proposal (16/10/19)
& Planning	Discuss final project idea with PS
	Research final project idea
	Final Project Proposal (30/10/19)
	Research field
	Research motors
Stage 2	Research movement options
Research	Research develepment boards
	Research power sources for project
	Research control methods
	Order initial components
	initial control of motor
Stage 3	Control speed of motors with MCU
Design and Build	Equations for motor and enviroments
	Design gear shaft end effector
	Design base of robot
	Design motor shield
	Design motor enclosure
	Assemble protoype of robot
	Write simple code to go up a flight of stairs
	Test initial protoype
	Implement on-board battery
	Add control methods for the robot ie. Space detection
	Code for methods of control
	Order additional conponents
	Make robot fully automated
	Order Final components
	Test robot
	Project Demo
	Research camera detection
Stage 4	Add camera to robot
Additional features	Add code for camera to detect objects
	Project Viva and Final Demo 13th and 14th of May 2020

Meetings